## Tasks Details
| Task Assigned | Total = 209 Completed = 183 InProgress = 8 Assigned = 12 Enhancement = 6
Id | Task Description | Assigned To | Status | Priority | Due Date | Actual Date | Desc.
1 | 1. Are we checking SLA missed? | sagar | completed | H
2 | 2. How is Nirav able to logon using mtc@corelogic.com? @Milan, aren't you using LDAP authentication? | nirav barot | completed | H
3 | 3. Channel filter is NOT working. | satish rabari | completed | H
4 | 4. Error report - is it showing correct values? | milan patel | completed | H
5 | 5. CHECK GRAMMAR BEFORE SHOWING MESSAGES, PLEASE GROW UP | nirav barot | completed | H
6 | 6. Daily Operations report - should we show only success or errors too? | milan patel | completed | H
7 | 7. PCI returns time EST, are we checking? | sagar | completed | H
8 | are we showing error loans in monthly recon report ? | milan patel | completed | H
9 | after uploading files console not stops atutomatically | sagar | completed | H
10 | in Search page remove loannumber and add businessfriendlyidname | satish rabari | completed | H | 2018-03-23 | 2018-03-22
11 | show Duedate in SLA error and show in Excel also | satish rabari | completed | H | 2018-03-23 | 2018-03-22
12 | summary control report date PM come in new line in columns | satish rabari | completed | H | 2018-03-23 | 2018-03-22 | depends on column
13 | summary control report : error text not showing | satish rabari | completed | H | 2018-03-23 | 2018-03-22
14 | SLA report - duedate filter not working | satish rabari | completed | H | 2018-03-23 | 2018-03-22
15 | search page report - change print date to shipped date | satish rabari | completed | H | 2018-03-23 | 2018-03-22
16 | date swaped - search report received on and printed on | satish rabari | completed | H | 2018-03-23 | 2018-03-22
17 | Date format not changed - in search page and pull back page (To -> to) | satish rabari | completed | H | 2018-03-23 | 2018-03-22
18 | create SP | akshar | completed | H | 2018-03-23 | 2018-03-22
19 | Remember Me, not working | satish rabari | completed | H | 2018-03-23 | 2018-03-22
20 | Clicking on AuthoMail should take us to home page | satish rabari | completed | H | 2018-03-23 | 2018-03-22
21 | Error status comes, but error text doesn't show up, On chart | satish rabari | completed | H | 2018-03-23 | 2018-03-22
22 | Show date in brackets on weekly chart | satish rabari | completed | H | 2018-03-23 | 2018-03-22
23 | Change Pull Back to Request Pullback, the button doesn't change color properly | satish rabari | completed | H | 2018-03-23 | 2018-03-22
24 | Collapse after go is clicked | satish rabari | Enhancement | H | 2018-03-23 | 2018-03-22
25 | Show error details on hover of error label | satish rabari | completed | H | 2018-03-23 | 2018-03-22
26 | Enter should work when there is one textbox only (pullback, login) | satish rabari | completed | H | 2018-03-23 | 2018-03-22
27 | Put Authorize att on pullback api | akshar | completed | H | 2018-03-23 | 2018-03-22
28 | SLA missed filter (only inprogress) not working | milan patel | completed | H | 2018-03-23 | 2018-03-22
29 | Invalid states (50 state) has bug , doesn't accept DC, is the list updated? | sagar | completed | H | 2018-03-23 | 2018-03-22
30 | figure out pullback access related issue. | akshar | completed | H | 2018-03-23 | 2018-03-22
31 | Add 'DocType' in search details popup. Heading "Document Type" everywhere. | satish rabari | completed | H | 2018-03-23 | 2018-03-22
32 | When will data come to Daily Data Operations report? | milan patel | completed | H | 2018-03-23 | 2018-03-22
33 | Test multiple pull back. | nirav barot | completed | H | 2018-03-23 | 2018-03-22
34 | Graph details, popup, show 'package name' in the details view, remove from batch view, why was it show in batch and not in detail?? | satish rabari | completed | H | 2018-03-23 | 2018-03-22
35 | Check integer format on "Weekly Batch Details" | satish rabari | completed | H | 2018-03-23 | 2018-03-22
36 | If we were sent 5+4 ZIP, make sure it is displayed on all reports and search screen, i.e. wherever ZIP code is displayed, it should show AS-IS | sagar | completed | H | 2018-03-23 | 2018-03-22 | it will show when data in database
37 | Confirm that pull backs are shown on the summary control report | milan patel | completed | H | 2018-03-23 | 2018-03-22
38 | all reports should be general, (Ex. Remove custmer identifier and request id which are come from AMC) | satish rabari | completed | H | 2018-03-23 | 2018-03-22
39 | weekly chart in progress details, change inprogess label button color from red to blue in pop up | satish rabari | completed | H | 2018-03-23 | 2018-03-22
40 | search page - list should be ordered by status as given in dropdown | satish rabari | completed | H | 2018-03-23 | 2018-03-22
41 | search page - create clear all filter | satish rabari | completed | H | 2018-03-23 | 2018-03-22
42 | pull back page - we show filter of "document type" but not in below listed table column | satish rabari | completed | H | 2018-03-24 | 2018-03-23
43 | pull back page - "received date" and "pullback requested" should be second or third in table after loan search, because when we go for pull back then we know loan number but we need "received date" because we search in multiple days then in which date this loan belong to is useful. | satish rabari | completed | H | 2018-03-24 | 2018-03-23
44 | remove extra comma in address and recipent name column | milan patel | completed | H | 2018-03-24 | 2018-03-23
45 | Mapping table for client with multiple domain | milan patel | Enhancement | H | 2018-03-24 | 2018-03-23
46 | show failed loans in weekly chart | satish rabari | completed | H | 2018-03-24 | 2018-03-23
47 | need to change "pulled back" status color, it is same as error color | satish rabari | completed | H | 2018-03-24 | 2018-03-23
48 | pullback icon alignment | satish rabari | completed | H | 2018-03-24 | 2018-03-23
49 | error SLA - column batch ids in filter contains wrong ids | satish rabari | completed | H | 2018-03-24 | 2018-03-27
50 | Summary control report, error report - change name id to perticular mail-piece id name | satish rabari | completed | H | 2018-03-28 | 2018-03-27
51 | common.clients - ClientName wrong designed | sagar | completed | H | 2018-03-28 | 2018-03-27
52 | Pullback should be consistent, use title case except column header | satish rabari | completed | H | 2018-03-28 | 2018-03-27
53 | why are we showing # in list details in pages, if not necessary then remove ? Discuss with ravibhai | satish rabari | completed | H | 2018-03-28 | 2018-03-27
54 | LOANNBR is it okay ? | satish rabari | completed | H | 2018-03-28 | 2018-03-27
55 | All (<Received Time> - <Batch Name>) , Label Name - "Filter by Batch"(bold as above labels) | satish rabari | completed | H | 2018-03-28 | 2018-03-27
56 | batch table fixed order of pipline status columns, acknowledge after validate | sagar | completed | H | 2018-03-28 | 2018-03-27
57 | batch status should be "Inprocess" after received | sagar | completed | H | 2018-03-28 | 2018-03-27
58 | get logo and replace it | satish rabari | completed | H | 2018-03-28 | 2018-03-27
59 | remove remember me from login screen | satish rabari | completed | H | 2018-03-28 | 2018-03-27
60 | request pull back button name should be - camel case, align text center | satish rabari | completed | H | 2018-03-28 | 2018-03-28
61 | put download icon at excel download | satish rabari | completed | H | 2018-03-28 | 2018-03-28
62 | put local word below reports date column name | satish rabari | completed | H | 2018-03-28 | 2018-03-28
63 | pull back page - date filter not working on same date | milan patel | completed | H | 2018-03-28 | 2018-03-28
64 | excel report button not on proper location | satish rabari | completed | H | 2018-03-28 | 2018-03-28
65 | not getting tracking details | satish rabari | completed | H | 2018-03-28 | 2018-03-28
66 | show process in while pulling back and while getting tracking details | satish rabari | completed | H | 2018-03-28 | 2018-03-28
67 | add due date in summary report should not be UTC | satish rabari | completed | H | 2018-03-28 | 2018-03-28
68 | weekly Chart pop up heading - Batch Summary Received On - 3/28/18 | satish rabari | completed | H | 2018-03-30 | 2018-03-30
69 | coloumn add - tota mail piece | satish rabari | completed | H | 2018-03-30 | 2018-03-30
70 | change button view to "View Details" | satish rabari | completed | H | 2018-03-30 | 2018-03-30
71 | increase height of pop up | satish rabari | completed | H | 2018-03-30 | 2018-03-30
72 | chart pop up - mail piece pop up heading - Mailpiece Summary Batch Id - #### Received On - ### (same as batch summary) | satish rabari | completed | H | 2018-03-30 | 2018-03-30
73 | add due date in above pop up (mm/dd)(time without seconds) | satish rabari | completed | H | 2018-03-30 | 2018-03-30
74 | pages shipped to Pages in above pop up | satish rabari | completed | H | 2018-03-30 | 2018-03-30
75 | create small tracking number in above pop up | satish rabari | completed | H | 2018-03-30 | 2018-03-30
76 | cross check sum of mail piece in mail piece chart | satish rabari | completed | H | 2018-03-30 | 2018-03-30
77 | date should not come in UTC format from database | satish rabari | completed | H | 2018-03-30 | 2018-03-30
78 | summary control - remove show error if there is no error | satish rabari | completed | H | 2018-03-30 | 2018-03-30
79 | recon - first date is wrong | satish rabari | completed | H | 2018-03-30 | 2018-03-30
80 | pull back reprt - status and Requested - swap | satish rabari | completed | H | 2018-03-30 | 2018-03-30
81 | pull report - replace loan no with mail piece id | satish rabari | completed | H | 2018-03-30 | 2018-03-30
82 | display batch error details in chart pop up | satish rabari | completed | H | 2018-03-30 | 2018-03-30
83 | space diff. in date written in title of summary control report (check in all reports) | satish rabari | completed | H | 2018-02-04 | 2018-02-04
84 | chart pop up title - add space after hiphen | satish rabari | completed | H | 2018-02-04 | 2018-02-04
85 | summary control report batch filter not working | satish rabari | completed | H | 2018-02-04 | 2018-02-04
86 | month recon report - we didn't provide channel name | satish rabari | Enhancement | H | 2018-02-04 | 2018-02-04
87 | search - only approval search is working | satish rabari | completed | H | 2018-02-04 | 2018-02-04
88 | daily operations report - remove batch id last column, change name batch id | satish rabari | completed | H | 2018-02-04 | 2018-02-04
89 | error sla on change doc. Type gives error | satish rabari | completed | H | 2018-04-04 | 2018-04-04
90 | month recon report - trackng number and method misplaced | satish rabari | completed | H | 2018-04-04 | 2018-04-04
91 | is it possible that in error mail piece doesn't contain shipping method details ? | satish rabari | completed | H | 2018-04-04 | 2018-04-04
92 | doc. Type problem in request pull back page | satish rabari | completed | H | 2018-04-04 | 2018-04-04
93 | chart - pop up wrong batch id | satish rabari | completed | H | 2018-04-04 | 2018-04-04
94 | is scan date should be local in tracking details ? | satish rabari | completed | H
95 | tracking details button - checked with adding entry in database | satish rabari | completed | H | 2018-04-05 | 2018-04-05
96 | Pullback whole batch (by client batch id as well search by date then pullback) |  | Enhancement | L | 2018-04-05 | 2018-04-05
97 | Batch report and batch search : by batch name, date etc. (when it was received, status, error desc, shipped time etc) |  | Enhancement | L | 2018-04-05 | 2018-04-05
98 | fedex tracking numbe shuold be open in new window | satish rabari | completed | H | 2018-04-05 | 2018-04-05
99 | Wednesday task - check tracking USPS on live site, get fedex prod. account | nirav barot | completed | H | 2018-04-05 | 2018-04-05
100 | USPS pro. Data query | akshar | completed | H | 2018-06-04 | 2018-06-04
101 | add 'U' or 'F' for USPS and FEDEX with Tracking number | satish rabari | Enhancement | H | 2018-07-04 | 2018-07-04
102 | delete UAT back up and delete it inform to AZIM | akshar | completed |  | 2018-07-04 | 2018-07-04
103 | change communication error message | satish rabari | completed |  | 2018-07-04 | 2018-07-04
104 | Quick pull bach - "No such records found in todays baches or pending batches" | satish rabari | completed |  | 2018-07-04 | 2018-07-04
105 | get authomail prod. Backup from azim and restore on UAT OR sync UAT database with Prod. | akshar | completed |  | 2018-07-04 | 2018-07-04
106 | Remove state list validation from packageinfo schema and move it to text file | sagar | completed | IMP | 2018-07-04 | 2018-07-04
107 | Validations: 1. XML Schema 2. Common Validations (AppCode, DocType, filename etc) 3. Client Specific validation | sagar | completed |  | 2018-07-04 | 2018-07-04
108 | Move ErrorReport and DeliveryReport methods to service layer | sagar | completed |  | 2018-07-04 | 2018-07-04
109 | 1. insert client code in USPS database otherwise shipping won't work | sagar | completed | IMP | 2018-07-04 | 2018-07-04
110 | 2. Fix code of USPS shipping label | sagar | completed | IMP | 2018-07-04 | 2018-07-04
111 | 3. Get Core process reviewed | sagar | completed | IMP | 2018-07-04 | 2018-07-04
112 | CreateFedexLabels.cs (remove hard coding of fedex URLs) | sagar | completed | IMP | 2018-07-04 | 2018-07-04
113 | Use Env.Prod (config. env) setting | sagar | completed | IMP | 2018-07-04 | 2018-07-04
114 | use relative paths | sagar | completed | IMP | 2018-07-04 | 2018-07-04
115 | use mailpiece id as customertransactionid | sagar | completed | IMP | 2018-07-04 | 2018-07-04
116 | use config.env in email subjects | sagar | completed | IMP | 2018-07-04 | 2018-07-04
117 | add AMC customer identifier mapping in database | sagar | completed | IMP | 2018-07-04 | 2018-07-04
118 | change pns batch naming convention - clientcode_doctypecode_printbatchno - clientcode_doctypecode_printbatchno - Can't go with this naming convention because length of batchname in pnsrequest gets failed. So it is good to use AppCode_PrintBatchNo | sagar | completed |  | 2018-07-04 | 2018-07-04
119 | deploy UAT on all web servers AND move 64 UAT to 57, as per Azeem's instructions | akshar | completed |  | 2018-07-04 | 2018-07-04
120 | no error - check hover message | nirav barot | completed |  | 2018-07-04 | 2018-07-04
121 | Pulled back' - pull back requested page - discuss with ravibhai | nirav barot | completed |  | 2018-08-04 | 2018-08-04
122 | 1. Why is batch status showing Error null? (discuss with ravibhai) | satish rabari | completed |  | 2018-09-04 | 2018-09-04
123 | 2. All dialog boxes on chart, closes when 'Esc' is pressed. Only the current one should close. | satish rabari | completed |  | 2018-09-04 | 2018-09-04
124 | 3. 'No error description' is still being displayed | satish rabari | completed |  | 2018-09-04 | 2018-09-04
125 | Check all reports : Change 'Error Code' column to 'Status' column, show error desc on hover when applicable (only when error), Pages Shipped should be 0 when status <> Shipped | satish rabari | completed |  | 2018-09-04 | 2018-09-04
126 | Does monthly recon, report show only shipped loans? Yes | satish rabari | completed |  | 2018-09-04 | 2018-09-04
127 | 6. I hope we are showing tracking details in descending order of 'Scan Date' | satish rabari | completed |  | 2018-09-04 | 2018-09-04
128 | 7. Check Excel export of all reports, make sure it is coming properly, it should get distorted because of comma (,) used in print location etc. | nirav barot | completed |  | 2018-09-04 | 2018-09-04
129 | use original CLUI css files, move all changes to a new class file if required. | satish rabari | completed |  | 2018-09-04 | 2018-09-04
130 | use csvstring to numbers which start with zero, for example tracking number | sagar | completed |  | 2018-09-04 | 2018-09-04
131 | use new naming convention for PnS batch, appcode_printbatchid | sagar | completed |  | 2018-09-04 | 2018-09-04
132 | keep tracking info button long enough so that when 'in progress' animation is shown, content doesn't move on screen | satish rabari | completed |  | 2018-09-04 | 2018-09-04
133 | error report - download excel - status column contain html | satish rabari | completed |  | 2018-09-04 | 2018-09-04
134 | setup UAT on all web servers and move UAT app to 57 | satish rabari | completed |  | 2018-09-04 | 2018-09-04
135 | Make absolutely sure that NO controller except Account is without 'Authorize' attribute., we don't want any security vulnerabilities. | satish rabari | completed |  | 2018-09-04 | 2018-09-04
136 | Let's remove admin@mtc.com COMPLETELY, add Akshar's login to admin role. | milan patel | completed |  | 2018-09-04 | 2018-09-04
137 | You can create admin@milestonetechnoconsulting.com if you want. | milan patel | completed |  | 2018-09-04 | 2018-09-04
138 | set chart pop up below border | satish rabari | completed |  | 2018-09-04 | 2018-09-04
139 | pages shipped - are we adding cover page or not ? - yes | milan patel | completed |  | 2018-09-04 | 2018-09-04
140 | AM batch status 'PulledBack' and PnS batch status 'PulledBack', DEFINE new statuses | sagar | completed |  | 2018-09-04 | 2018-09-04
141 | increase height of todays batch graph and move quick back below weekly chart | satish rabari | completed |  | 2018-09-04 | 2018-09-04
142 | discuss with brijesh - should we show pullback in this reports - 1. 1. Dailt op. 2. error 3. error sla. 4. summay 5. monthly recon 6. pulled back request - show only summary control report | akshar | completed |  | 2018-09-04 | 2018-09-04
143 | create script for database cleaning in production | milan patel | completed |  | 2018-09-04 | 2018-09-04
144 | send an email to azim for backup | akshar | completed |  | 2018-09-04 | 2018-09-04
145 | do not store stack strace in database, store in log file - contact to ravibhai | sagar | completed |  | 2018-09-04 | 2018-09-04
146 | create hover error - with read only property - it should be 2 line error joined by new line | milan patel | completed |  | 2018-09-04 | 2018-09-04
147 | check "business id" drop down after inserting insurance number - text box not shown properly | satish rabari | completed
148 | pull back page - column click ordering stoped | satish rabari | completed |  | 2018-04-11 | 2018-04-11
149 | QC ALL reports, check every time when new verion release | nirav barot | inprogress |  | 2018-04-11 | 2018-04-11
150 | compare report with old reports | nirav barot | completed |  | 2018-04-11 | 2018-04-11
151 | STOP reporting job ON production - remove triggers | sagar | completed |  | 2018-04-11 | 2018-04-11
152 | DO NOT clean PROD database | akshar | completed |  | 2018-04-11 | 2018-04-11
153 | mark all loans as reportedback in production, so that reports don't go again | sagar | completed |  | 2018-04-11 | 2018-04-11
154 | create list of UI changes | nirav barot | completed |  | 2018-04-11 | 2018-04-11
155 | solve chart UI bug | satish rabari | completed |  | 2018-04-11 | 2018-04-11
156 | Monitor pending batches: 9 PM EST, send email to brijesh, devang, ravi, sagar, Akshar | milan patel | inprogress |  | 2018-04-11 | 2018-04-11
157 | Use AMC error codes | sagar | completed |  | 2018-04-11 | 2018-04-11
158 | Send sample summary report to Brijesh without fail | akshar | completed |  | 2018-04-11 | 2018-04-11
159 | Update error code map as per old AMC | sagar | completed |  | 2018-04-11 | 2018-04-11
160 | Summary report - Show error code and description in a single column. | satish rabari | completed |  | 2018-04-11 | 2018-04-11
161 | Please make sure you create smoke2.txt and write notes for our second release | all | completed |  | 2018-04-11 | 2018-04-11
162 | Check all pdf files created in prod run, make sure cover page template is proper, make sure address and borrower name is accurate. Make sure pdf content is accurate. Must do today | nirav barot | completed |  | 2018-04-11 | 2018-04-11
163 | please check with Milan if he is ignoring 'Pullback' mail pieces in SLA missed , or in other words which mail piece status are SHOWN in SLA missed, pls confirm with me | milan patel | completed |  | 2018-04-12 | 2018-04-12
164 | plan for PulledBack status of batch, esp in chart | all | completed |  | 2018-04-12 | 2018-04-12
165 | after testing, update core and console on UAT environment | sagar | completed |  | 2018-04-12 | 2018-04-12
166 | Quick pull back - check for mailpiece status Shipping Status Pull back requested Pullback no Shipped no | satish rabari | completed |  | 2018-04-12 | 2018-04-12
167 | Smoke -2, - Stagging, internal and prod. Ma doc. Type and descript. size 512 length karvi (Query - update AM.MailPieces set doctypeid = null where doctypeid = 0) - Task schedular - monitor and core - give "startin" | akshar | completed | V.IMP | 2018-04-12 | 2018-04-12
168 | Pull back reporting decide whether to enable or not ? (pullback enable કરવું કે નઈ?) | sagar | completed |  | 2018-04-12 | 2018-04-12
169 | create change password page | milan patel | completed |  | 2018-04-12 | 2018-04-12
170 | hover over msg. should be opened in proper manner. It opened now out of page | satish rabari | completed |  | 2018-04-14 | 2018-04-14
171 | pull back thay to report ma tracking number nai java devano | sagar | completed |  | 2018-04-14 | 2018-04-14
172 | chart - 0 value based color shown in so remove it | satish rabari | completed |  | 2018-04-14 | 2018-04-14
173 | DEMO - for Alaska - COMMOM.Setting - search in - for msg.s if there Is client name USAA used any where - mail batc.validation error table - search in - error desc. Search in - search in visual studio - get batch .pdf from alaska production | nirav barot | completed |  | 2018-04-14 | 2018-04-14
174 | Test Case Change PWD login to authomailusing corelogic acc. Change password test fun. Test in runninng authomail tab logout from authomail attempt login with old passwrod one time login with new password check change password messages | nirav barot | completed |  | 2018-04-14 | 2018-04-14
175 | search "core logic" word in system | milan patel | completed |  | 2018-04-14 | 2018-04-14
176 | <compilation … debug="true" /> and/or <trace enabled="true" … /> check settings sent above , In web.config | milan patel | completed |  | 2018-04-16 | 2018-04-16
177 | determine how much memory console and core eat up | milan patel | completed |  | 2018-04-16 | 2018-04-16
178 | publish web code in release mode, turn debugging off | milan patel | completed |  | 2018-04-16 | 2018-04-16
179 | host a plain asp.net mvc site with web api on 57 and check its memory usage (Akshar and Milan) | akshar , milan | completed |  | 2018-04-16 | 2018-04-16
180 | use HostingEnvironment.MapPath or Server.MapPath to get absolute path, store only relative path in the config setting (Akshar) | akshar | completed |  | 2018-04-16 | 2018-04-16
181 | 404 woff2 | satish rabari | completed |  | 2018-04-16 | 2018-04-16
182 | pns service, log batch name when queue is queried | sagar | completed |  | 2018-04-16 | 2018-04-16
183 | Monitor pending batches: 6 PM and 9 PM IST, send email to brijesh, devang, ravi, sagar, akshar (automated notification) | milan patel | inprogress |  | 2018-04-16 | 2018-04-16
184 | profiling - to check memory eaten by system ? | satish rabari | completed |  | 2018-04-17 | 2018-04-17
185 | 12. Perform mild load test on website, simultaneously click on login button, 10 people | all | completed |  | 2018-04-17 | 2018-04-17
186 | add "client name" in UI , put mainly name from database not client code , change name of all client as in their website | satish rabari | inprogress |  | 2018-04-17 | 2018-04-17
187 | select * from ( select deptid, count(id) as empcount from emp group by deptid having count(id) = (select max(empcount) as maxempcount from (select deptid, count(id) as empcount from emp group by deptid)t1)) t3, dept where t3.deptId = dept.id | ravi | inprogress
188 | site slow | satish rabari | completed |  | 2018-04-19 | 2018-04-19
189 | remove new line chars from report | sagar | completed |  | 2018-04-19 | 2018-04-19
190 | compare 300 records = 1.7 mb after changes it will be in kb.s | milan patel | completed |  | 2018-04-20 | 2018-04-20
191 | Create unique index on ALL GUID fields in ALL tables, prepare a list and show me. The script to create unique index must be stored in database scripts and must be run in QA, Staging and Production. If duplicates are found, contact me to resolve. Before you create indexes, check for duplicates in staging and prod databases. If found, report to me. | milan patel | inprogress |  | 2018-04-20 | 2018-04-20
192 | Sagar : Do we have scripts to create composite unique indexes in doctype table (client id and doctypcode) AND (client id and doctype desc) in tfs? Do we have script to make doctypeid primary key in tfs? We have run these scripts in production but they should all be in tfs | sagar | completed |  | 2018-04-20 | 2018-04-20
193 | Nirav - VERY IMPORTANT : Use database scripts we have in tfs (after the above tasks are complete), and create a database. Compare this database (column by column including column datatype and nullable, PK, FK, UK etc., stored procs etc.) with production database (106). Do this carefully, take Vijaybhai's help if necessary. But I want to make sure they have checked in everything, NOTHING is missed out. | nirav barot | inprogress |  | 2018-04-20 | 2018-04-20
194 | error report - error on hover get cut down (compare with search error records) | satish rabari | Assigned
195 | search page - if insurance number added in to the search drop down then in search result it should show as loan number / insurance number | satish rabari | Assigned
196 | test for multiple client - create menu in home page for diff. clients | satish rabari | inprogress
197 | last login client name not stored | satish rabari | Assigned
198 | daily detail operation report - Alaska - channel filter empty | satish rabari | completed
199 | pull back - spinner shows even if mail piece already pulled back | satish rabari | Assigned
200 | Tasks for Akshar 1. Delfus letters email 2. change host URL in prod Akshar Pls make sure to change the host URL (sftp url) to below in CondoSafe Job – mft.corelogic.com | akshar | Assigned
201 | Task Milan : Change message, in tfs, QA, Staging and Prod instead of " You may use traditional ways to change your password like 'Ctrl + Alt + Del' on your computer" use such as instead of like | milan patel | completed
202 | "The User Name field is required.", "The Password field is required." remove field word if not needed | milan patel | Assigned
203 | label stays as long In login page - 'insert user name' | milan patel | Assigned
204 | on lock out account it refresh continuously | milan patel | Assigned
205 | MOST IMP FEATURE, add this in your task, assign to Sagar, Milan, Satish, Akshar: Prepare a page to record all exceptions and show them on a support webpage in AuthoMail. | all | Assigned
206 | BUG on login page: mailto:documentservices@corelogic.com?subject=AuthoMail.com Inquiry | satish rabari | Assigned
207 | filter by batch - all (time - batch name) - we do not have batch name in table details | satish rabari | Assigned
208 | login page - put forgot password below password box | satish rabari | Assigned
209 | business unit details active value changed on closing pop up | satish rabari | completed

## EST time formula
duedate = (receivedon > (date(receivedon) + cut off) ? date(receivedon) (23:59:59) EST + sladays + 1 : date(receivedon) (23:59:59) EST + sladays
duedate = convert to UTC and store in db
duedate = (receivedon.ToEst > (date(receivedon.toest) + cut off) ? date(receivedon.toest) (23:59:59) EST + sladays + 1 : date(receivedon) (23:59:59) EST + sladays
receivedon = 2018-03-20 03:30:00 UTC.toEst = 2018-03-19 23:30:00 EST
23:30:00 EST > 19:45:00 EST ? yes
date(receivedon.toest) (23:59:59) EST + sladays + 1
2018-03-19 23:59:59 EST + 0 + 1 = 2018-03-20 23:59:59 EST
|  | +5' | +5.30' | Day light saving
|  | +4' | +5.30' | without day light saving
AuthMail | 10.212.40.106
AuthomailUser
Authomail@User
Autho Mail-UAT | 10.215.176.81
AuthomailUser
Authomail@User
UAT | 10.215.112.64
sandpatel
પાસવર્ડ એટ ૩
Passcode4
Testing for multiple USERS
Alaska User
K.Hoggard@alaskausa.org
Client@123

## update scripts
UPDATE QUIRIED
| update [AuthoMail_UAT].[Common].[SystemSettings] set Value = '\\Mstc-neelkanth\c$\MSTC\ADE_PnS' where id = 'Core_PnS_SFT_HostURL' | recycle authomail database
update [AuthoMail_UAT].[Common].[SystemSettings] set Value = '\\Mstc-neelkanth\c$\MSTC\ADE_PnS' where id = 'Core_PnS_SFT_RootDir'
| update [Common].[SystemSettings] set Value='E:\TFS\AuthoMail\source\AuthoMail\AM.Web\Template\PullBackForm.pdf' Where Id='API_PB_PullBackFormTemplatePath' | DELETE FROM [PnS].LogBatchTimeLine DELETE FROM [PnS].MRDFResponse DELETE FROM [PnS].MRDFRequest DELETE FROM [PnS].BatchSummary DBCC CHECKIDENT('[PnS].BatchSummary', RESEED, 1000) DELETE FROM [Common].[MailPiecePageInfo] DELETE FROM [AM].[LogBatchTimeLine] DELETE FROM [AM].[MailPieceCustomInfo] DELETE FROM [AM].[MailPieces] DELETE FROM [AM].[PrintBatches] DBCC CHECKIDENT('[AM].[PrintBatches]', RESEED, 1000) DBCC CHECKIDENT('[AM].[MailPieces]', RESEED, 1000) DELETE FROM [AM].[MailBatchCustomInfo] DELETE FROM [AM].[MailBatches] DBCC CHECKIDENT('[AM].[MailBatches]', RESEED, 1000)
update [Common].[SystemSettings] set Value='nirav.barot@milestonetechnoconsulting.com' Where Id='API_Email_Cc'
update [Common].[SystemSettings] set Value='nirav.barot@milestonetechnoconsulting.com' Where Id='API_Email_To'
update [AuthoMail].[Common].[SystemSettings] set value = 'Internal' where id = 'Environment'
update [Common].[SystemSettings] set Value='\\MTC-NIRAVB\c$\MSTC\AM\AMC' Where Id='AMCDirPath'
update [Common].[SystemSettings] set Value='E:\TFS\AuthoMail\source\AuthoMail\AM.Console\bin\Debug\AuthoMailRoot' Where Id='AuthoMailRootFolder'
update [Common].[SystemSettings] set Value='E:\TFS\AuthoMail\source\AuthoMail\AM.Core\CoverTemplates' Where Id='CoverTemplateFolder'
update [Common].[SystemSettings] set Value='E:\TFS\AuthoMail\source\AuthoMail\AM.Console\HTMLTemplates\DET.html' Where Id='DSEmailTemplate'
update [Common].[SystemSettings] set Value='E:\TFS\AuthoMail\source\AuthoMail\AM.Console\HTMLTemplates\PLET.html' Where Id='PSEmailTemplate'
update [AuthoMail].[Common].[SFTChannels] set host = '\\MTC-NIRAVB\c$\MSTC\AM\USAA' where code = 'AMC_Internal'
Flow of autho mail - folder details | Flow AuthoMail To PnS Service AuthoMail Side AM Batch Download - AMRequest AM Batch Process - PnSRequest PnS Service Batch To Process through PnSService - ADE_PnS/ClientCode/Batch PnS Service Side Download Batch for Processing path - ADE_PnS/ClientCode/Batch PnS Batch Download - PnSRequest PnS Batch Process to Submit to PCI - PCIRequest PCI MRDF Response to Process - PCIResponse PnS response generate from PCI MRDF response file - PnSResponse PnS response copy to Pns batch submitted folder with trigger file - ADE_PnS/ClientCode AuthoMail Side PnSService Response processed by AM - AMRoot/ClientCode/PnSResponses AM Batch Response report to Client - AMResponse
CREATE GUID | DECLARE @myid uniqueidentifier SET @myid = NEWID() PRINT CONVERT(varchar(255), @myid)
SELECT pipelinestatus, * FROM [AuthoMail_UAT].[AM].[MailBatches] where id in (4005) order by id desc SELECT shippingstatus, * FROM [AM].[MailPieces] where mailbatchid in (4005) order by id desc

## SQL Queries
select [BatchStatus] ,[PipelineStatus],* from [AM].[MailBatches] where Id in (1151) --where BatchName = '636573520218250599' --order by ID desc
select [ShippingStatus],[ErrorCode],[ErrorDesc],* from [AM].[MailPieces] where businessfriendlyidvalue = '3000080816' and MailBatchId = 1151 --where MailBatchId = 1013 order by ID desc
SELECT * FROM [AuthoMail_UAT].[Common].[SystemSettings] --where id = 'PnS_SFT_HostURL'
select [ShippingStatus],[ErrorCode],[ErrorDesc],* from [AM].[MailPieces] where businessfriendlyidvalue = '3000080816' and MailBatchId = 1151 --where MailBatchId = 1013 order by ID desc
/****** Script for SelectTopNRows command from SSMS ******/ SELECT * FROM [AuthoMail_UAT].[Common].[SystemSettings] --where id = 'PnS_SFT_HostURL'
ADD TRACKING DETAILS SET IDENTITY_INSERT [dbo].[tblUSPSTrackingInfo] ON INSERT [dbo].[tblUSPSTrackingInfo] ([ID], [UploadLogID], [FacilityID], [OperationCode], [ScanDate], [RoutingCode], [TrackingCode]) VALUES (1, 1, N'92199', N'142', CAST(N'2016-06-01 22:38:17.000' AS DateTime), N'59715', N'00310901599685000393') GO
SET IDENTITY_INSERT [dbo].[tblUSPSTrackingInfo] OFF UPLOAD LOG ENTRY - 1 wfsb68a1708.pkg 2016-06-09 14:19:45.713
find due date select * from [AM].[MailPieces] where mailbatchid in ( select id from [AM].[MailBatches] --where batchname = '636573520218250599' where receivedon > '2018-03-27 19:09:56.000') --and shippingstatus = 'error' and MailBatchId =1013
select [BatchStatus] ,[PipelineStatus],receivedon,* from [AM].[MailBatches] --where Id in (1151) where BatchName = '636573538244524375' --order by ID desc select [ShippingStatus],PrintedOn, ShippedOn,[ErrorCode],[ErrorDesc],DueDate,documentorpackagetype, * from [AM].[MailPieces] --where businessfriendlyidvalue = '3000080816' and MailBatchId = 1151 where MailBatchId = 1016 --and uniqueid = '0d5a7147-6749-4f08-afcf-011c01c5a4a5' --where documentorpackagetype = 'approval' --order by ID desc
generate new GUID | DECLARE @myid uniqueidentifier SET @myid = NEWID() PRINT CONVERT(varchar(255), @myid)
Complete flow of autho mail | Flow AuthoMail To PnS Service AuthoMail Side AM Batch Download - AMRequest AM Batch Process - PnSRequest PnS Service Batch To Process through PnSService - ADE_PnS/ClientCode/Batch PnS Service Side Download Batch for Processing path - ADE_PnS/ClientCode/Batch PnS Batch Download - PnSRequest PnS Batch Process to Submit to PCI - PCIRequest PCI MRDF Response to Process - PCIResponse PnS response generate from PCI MRDF response file - PnSResponse PnS response copy to Pns batch submitted folder with trigger file - ADE_PnS/ClientCode AuthoMail Side PnSService Response processed by AM - AMRoot/ClientCode/PnSResponses AM Batch Response report to Client - AMResponse
Due Date Query | select m.id,m.uniqueid,m.DocTypeId,m.Documentorpackagetype,mb.receivedon,m.duedate,m.ErrorCode,d.bizdaycutoff,d.bizdayslatype,d.bizdaytimespan,d.satcutoff,d.satslatype,d.sattimespan,d.suncutoff,d.sunslatype,d.suntimespan from [AM].[MailBatches] mb, [AM].[MailPieces] m left outer join [AM].[DocTypes] d ON m.DocTypeId=d.Id where mb.Id=m.[MailBatchId] and m.errorcode != 'No_Error' --and m.doctypeid is null --and m.duedate is null --or and m.errorcode != 'No_Error' and m.doctypeid is not null and m.duedate is not null -- m.doctypeid is not null and m.DueDate is not null --and m.doctypeid is not null and m.DueDate is null --and m.doctypeid is null and m.DueDate is null order by id asc
shipped partial validated
3 record extra in db of doc type "AdverseAction" | select m.id,m.shippingstatus,m.SLADays,m.duedate,m.DocTypeId,m.Documentorpackagetype,mb.receivedon,mb.validationstatus,m.duedate,m.ErrorCode,m.errordesc,d.bizdaycutoff,d.bizdayslatype,d.bizdaytimespan,d.satcutoff,d.satslatype,d.sattimespan,d.suncutoff,d.sunslatype,d.suntimespan from [AM].[MailBatches] mb, [AM].[MailPieces] m left outer join [AM].[DocTypes] d ON m.DocTypeId=d.Id where mb.Id=m.[MailBatchId] and sladays < -1 and mb.receivedon > '2018-07-25 03:59:59.000' and mb.receivedon < '2018-07-26 03:59:59.000' and mb.validationstatus = 'valid'
SLA missed Records by day | select m.id,m.shippingstatus,m.SLADays,mb.receivedon,m.duedate,m.DocTypeId,m.Documentorpackagetype,mb.validationstatus,m.duedate,m.ErrorCode,m.errordesc,d.bizdaycutoff,d.bizdayslatype,d.bizdaytimespan,d.satcutoff,d.satslatype,d.sattimespan,d.suncutoff,d.sunslatype,d.suntimespan from [AM].[MailBatches] mb, [AM].[MailPieces] m left outer join [AM].[DocTypes] d ON m.DocTypeId=d.Id where m.[MailBatchId] = mb.Id and sladays < 0 and mb.receivedon > '2018-07-27 03:59:59' and mb.receivedon < '2018-07-28 03:59:59' and m.clientid = 101 AND m.ShippingStatus IN ('InProgress','Shipped','Error')
Total Batch | select * from am.MailBatches where receivedon > '2018-07-28 03:59:59' and receivedon < '2018-07-29 03:59:59' and clientid = 101
STATUS | select m.id,m.shippingstatus,m.DocTypeId,m.Documentorpackagetype,mb.receivedon,m.ShippedOn,mb.validationstatus,m.duedate,m.ErrorCode,m.errordesc from [AM].[MailBatches] mb, [AM].[MailPieces] m left outer join [AM].[DocTypes] d ON m.DocTypeId=d.Id where m.[MailBatchId] = mb.Id --and sladays < 0 AND m.ShippingStatus not IN ('Error') and mb.receivedon > '2018-08-12 03:59:59' and mb.receivedon < '2018-08-13 03:59:59' and m.clientid = 101 AND m.ShippingStatus IN ('inprogress') --AND m.ShippingStatus IN ('Error') ---AND m.ShippingStatus IN ('shipped')
SLA Days
select m.id,m.shippingstatus,m.DocTypeId,m.Documentorpackagetype,mb.receivedon,mb.validationstatus,m.duedate,m.ErrorCode,m.errordesc,d.bizdaycutoff,d.bizdayslatype,d.bizdaytimespan,d.satcutoff,d.satslatype,d.sattimespan,d.suncutoff,d.sunslatype,d.suntimespan from [AM].[MailBatches] mb, [AM].[MailPieces] m left outer join [AM].[DocTypes] d ON m.DocTypeId=d.Id where mb.Id=m.[MailBatchId] --and mb.receivedon > '2018-07-27 03:59:59' and mb.receivedon < '2018-07-28 03:59:59' and mb.ClientId = 101 --and m.shippingstatus <> 'Shipped' and m.id in (18972, 18822, 19020, 19061, 19013, 19314, 20084, 19402) --select * from [AM].[DocTypes] where Id = 69
HSBC
DocTypes | select * from [AM].[DocTypes] where clientid = 104
Batches | select * from am.MailBatches where receivedon > '2018-07-28 03:59:59' and receivedon < '2018-07-29 03:59:59' and clientid = 104
Mail Pieces - all status | select m.businessfriendlyidvalue,mb.batchname,m.shippingstatus,mb.receivedon,m.duedate,m.shippedon,m.DocTypeId,m.Documentorpackagetype,m.errordesc from [AM].[MailBatches] mb, [AM].[MailPieces] m left outer join [AM].[DocTypes] d ON m.DocTypeId=d.Id where m.[MailBatchId] = mb.Id and sladays < 0 AND m.ShippingStatus not IN ('Error') and mb.receivedon > '2018-08-1 03:59:59' and mb.receivedon < '2018-08-2 03:59:59' and m.clientid = 104 --AND m.ShippingStatus IN ('inprogress') --AND m.ShippingStatus IN ('Error') ---AND m.ShippingStatus IN ('shipped')
Clean Database | DELETE FROM [Common].[MailPiecePageInfo] DELETE FROM [PnS].LogBatchTimeLine DELETE FROM [PnS].MRDFResponse DELETE FROM [PnS].MRDFRequest DELETE FROM [PnS].BatchSummary DBCC CHECKIDENT('[PnS].BatchSummary', RESEED, 1000) DELETE FROM [Common].[MailPiecePageInfo] DELETE FROM [AM].[LogBatchTimeLine] DELETE FROM [AM].[MailPieceCustomInfo] DELETE FROM [AM].[PullBackRequests] DELETE FROM [AM].[MailPieces] DELETE FROM [AM].[PrintBatches] DBCC CHECKIDENT('[AM].[PullBackRequests]', RESEED, 0) DBCC CHECKIDENT('[AM].[PrintBatches]', RESEED, 1000) DBCC CHECKIDENT('[AM].[MailPieces]', RESEED, 1000) DELETE FROM [AM].[MailBatchCustomInfo] DELETE FROM [AM].[MailBatches] DBCC CHECKIDENT('[AM].[MailBatches]', RESEED, 1000)
Get Dallas mail pieces details | select * from [AM].[MailPieces] where mailbatchid in (select id from am.MailBatches where receivedon > '2018-08-7 03:59:59' and receivedon < '2018-08-8 03:59:59' and clientid = 101) and printlocation like '%dallas%'
Revert to Prepped Stage All Batches DELETE FROM AM.PrintBatches DBCC CHECKIDENT('[AM].[PrintBatches]', RESEED, 1000) UPDATE AM.MailPieces SET PrintBatchId=NULL WHERE ShippingStatus='InProgress' UPDATE AM.MailBatches SET SubmittedToShippingOn=NULL, ShippingResponseReceivedOn=NULL, PipelineStatus='Prepped' WHERE ValidationStatus IN ('Valid','PartiallyValid')
select m.businessfriendlyidvalue,d.DocTypeCode,MissedSLAreason, DATEADD(HOUR,-4,mb.receivedon) as Received, DATEADD(HOUR,-4,bs.submittedon) as Submitted, DATEADD(HOUR,-4,m.shippedon) as Shipped , DATEADD(HOUR,-4,m.duedate) as DueDate, Datediff(minute,mb.receivedon,bs.submittedon) as [Diff in Minutes], m.printlocation, m.MissedSLAReason, m.shippingstatus, m.DocTypeId, m.Documentorpackagetype from [AM].[MailBatches] mb,[AM].[MailPieces] m left outer join [AM].[DocTypes] d ON m.DocTypeId=d.Id left outer join [PnS].[MRDFRequest] as r on m.uniqueid = r.uniqueid left outer join [PnS].[BatchSummary] as bs on r.jobid = bs.printbatch where m.[MailBatchId] = mb.Id AND m.ShippingStatus not IN ('Error') and (m.MissedSLAReason <> 'NA' or m.MissedSLAReason is null) and m.SLADays<0 and mb.receivedon between '2018-12-27 03:59:59' and '2018-12-28 03:59:59' and m.clientid = 104

## AuthoMail-UAT Versions Updates
Sr. No | Project Name | Version number | Features for UAT | Features for production | Developer
1 | AuthoMail_UAT | v.-- | * Search Page - (Query Design) 1 new filter added - tracking number | * Search Page - (Query Design) 3 new filter added 1.clientbatchid 2.mailbatchid 3.trackingno * Account module - - new 2 role added 1.ClientUserManager 2.CorelogicUserManager - UI created to assign above role using Admin login - details shown of registration request Approve, Reject or Pending - sending email on new registration, waiting for approval and rejection * Report Page - MonthlyReconreport mailpiece PDF file link shown to download pdf | Milan
|  |  | * AM Console HSBC Code * AM Core Process AM, Due Date Logic, Due Date logic for PnSRequest * PnS Service ByPass PCI | same | Sagar
|  |  | Search Screen: -Search by Tracking number -View MailPiece details on Loannumber click issue fixed | Search Screen: -Search by Tracking number, Batch Id, Client Batch Id -View MailPiece details on Loannumber click -Show tracking details on new page (click on tracking number inside View Details of MailPiece modal) Report -SummaryControlReport:remove cutoff time -Monthly Recon Add pdf received file | Satish
| Deployment check |  | Take watch in Config file and test tracking number (web barcode app cofig.)

## Doc Type Table
USPS
Id | DocTypeCode | ClientId | PrintSize | ContentScalePercent | PrintFormat | QCPercent | ShippingCarrier | ShippingServiceType | ShippingAccountCode | IsReturnInfoSpecified | RetRcptPrefix | RetRcptFirstName | RetRcptMiddleName | RetRcptLastName | RetRcptSuffix | RetRcptPhone | RetRcptOrganization | RetRcptAddrOptionalLine1AboveStreet | RetRcptAddrOptionalLine2AboveStreet | RetRcptAddressStreet | RetRcptAddressAptOrSuiteOrOther | RetRcptAddrOptionalLine1BelowStreet | RetRcptAddrOptionalLine2BelowStreet | RetRcptAddressCity | RetRcptAddressState | RetRcptAddressZIP | ClientEmails | ClientContactNo | SupportEmails | SupportContactNo | IsActive | ModifiedOn | CreatedOn | CreatedBy | ModifiedBy | Description | BizdayCutOff | BizdaySLAType | BizdayTimeSpan | SatCutOff | SatSLAType | SatTimeSpan | SunCutOff | SunSLAType | SunTimeSpan
65 | Approval | 101 | LETTER-IP | 100 | Simplex | 0 | USPS | USPS | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 43159.5483 | 43158.5483 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | Approval | 0:00 | Duration | 01:00:00:00 | 0:00 | Duration | 01:00:00:00 | NULL | NA | NULL
70 | LPMIDisclosures | 101 | LETTER-IP | 100 | Simplex | 0 | USPS | USPS | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 43159.5483 | 43158.5483 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | LPMI Disclosures | 0:00 | Duration | 01:00:00:00 | 0:00 | Duration | 01:00:00:00 | NULL | NA | NULL
71 | PreApprovalPackage | 101 | LETTER-IP | 100 | Simplex | 0 | USPS | USPS | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 43159.5483 | 43158.5483 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | Pre Approval | 0:00 | Duration | 01:00:00:00 | 0:00 | Duration | 01:00:00:00 | NULL | NA | NULL
87 | AppraisalReportWaiver_E | 101 | LETTER-IP | 100 | Simplex | 0 | USPS | USPS_EXPRESSMAIL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 43159.5483 | 43158.5483 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | Appraisal Report Waiver-ExpressMailing | 15:00 | FixedTime | 00:23:59:59 | 15:00 | FixedTime | 00:23:59:59 | NULL | NA | NULL
89 | StandAloneLoanEstimate_E | 101 | LETTER-IP | 100 | Simplex | 0 | USPS | USPS_EXPRESSMAIL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 43159.5483 | 43158.5483 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | Stand Alone - Loan Estimate-ExpressMailing | 15:00 | FixedTime | 00:23:59:59 | 15:00 | FixedTime | 00:23:59:59 | NULL | NA | NULL
90 | InitialDisclosures_E | 101 | LETTER-IP | 100 | Simplex | 0 | USPS | USPS_EXPRESSMAIL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 43159.5483 | 43158.5483 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | Initial Disclosures-ExpressMailing | 15:00 | FixedTime | 00:23:59:59 | 15:00 | FixedTime | 00:23:59:59 | NULL | NA | NULL
FedEx
67 | AppraisalReportWaiver | 101 | LETTER-IP | 100 | Simplex | 0 | FedEx | PRIORITY_OVERNIGHT | USAA_PROD | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 43159.5483 | 43158.5483 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | Appraisal Report Waiver | 19:00 | FixedTime | 00:23:59:59 | 12:00 | FixedTime | 00:23:59:59 | NULL | NA | NULL
69 | InitialDisclosures | 101 | LETTER-IP | 100 | Simplex | 0 | FedEx | PRIORITY_OVERNIGHT | USAA_PROD | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 43159.5483 | 43158.5483 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | Initial Disclosures | 19:00 | FixedTime | 00:23:59:59 | 12:00 | FixedTime | 00:23:59:59 | NULL | NA | NULL
73 | StandAloneLoanEstimate | 101 | LETTER-IP | 100 | Simplex | 0 | FedEx | PRIORITY_OVERNIGHT | USAA_PROD | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 1 | 43159.5483 | 43158.5483 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | 66f8d3e7-b66a-48d9-911f-d3914f1b3a11 | Stand Alone - Loan Estimate | 19:00 | FixedTime | 00:23:59:59 | 12:00 | FixedTime | 00:23:59:59 | NULL | NA | NULL

## Dallas Test Case
sr. | Case | Description | Expected Results
| test scanning app | get batch with more then 50 mail pieces • create .pdf file by merging .pdfs them all In single .pdf file
| console app | check whther print location is updated or not In table
| mail piece table | check print location column • Design - mailpiece table, type unique column • check update on getting dallas type mail pieces
| Create Batch | • ALASKA, HSBC and USAA - all with 50 mailpieces • create fedex batch with time ♦ downloaded time - 4.58pm, 7.58 ♦ downloaded time - 5.02pm , 8.02 ♦ before cut off and after cut off ♦ downloaded on - 8.05pm | ♣ Downloded before 5pm - send to PCI ♣ Downloded after 5pm - send to Dallas ♣ Downloded before 8pm - send to dallas ♣ Downloded after 8pm - send to pci
| pullBack | Algo - if PrintLocation "PCI" then Only send email of PullBackRequest.
| scanner setup | configure all - required smart phones with scan app in mahesh and dhaval comp
| test all clients | test parallay all 3 clients in 3 computers
| tell to satish | remove all prefix 0 in barcode for testing

## Sheet1
| ShippingServiceType |  |  | Total
1 | fedex | fixed time | QC | 16 | FedexFixedTime
2 | fedex | fixed time | no QC
1 | USPS | duration | QC | 5 | USPSDuration
2 | USPS | duration | no QC
1 | USPS_EXPRESSMAIL | fixed time | QC | 4 | USPSFixedTime
2 | USPS_EXPRESSMAIL | fixed time | no QC